## Project Overview
🏦 Banking Application — Manual Testing Project
Project follows 10 Standard QA Steps ¦ Application: Core Banking System ¦ Version: 1.0
Project Name |  | Banking Application Manual Testing
Application Type |  | Web + Mobile Banking Platform
Testing Type |  | Manual Testing (Functional, Security, Regression, UAT)
Total Features |  | 15 Banking Modules
Total Test Cases |  | 25 Test Cases
QA Environment |  | SIT + UAT
Project Duration |  | 4 Weeks (Sprint-based)
Tool Used |  | JIRA (Bug Tracking) ¦ TestRail (Test Management) ¦ Excel (Documentation)
Prepared By |  | QA Team
Date |  | April 2026
📋 10 QA Steps Followed in This Project
Step | Phase |  | Description / Deliverables
Step 1 | Project Introduction |  | Understand project scope, objectives, and stakeholders. Review BRD/SRS documents.
Step 2 | Understanding & Explore Functionality |  | Explore all 15 banking features, study user flows, API docs, and UI wireframes.
Step 3 | Test Plan → Estimation |  | Create Test Plan with scope, schedule, resources, risks, and effort estimation.
Step 4 | Writing Test Scenarios |  | Write high-level test scenarios for each feature covering positive & negative cases.
Step 5 | Writing Test Cases & Reviews |  | Detailed test cases with steps, data, expected results. Peer review & sign-off.
Step 6 | Environment Setup & Build Deployment |  | Configure SIT/UAT environments, deploy build, verify smoke test pass.
Step 7 | Test Execution |  | Execute all test cases, record actual results, capture screenshots for failures.
Step 8 | Bug Reporting & Tracking |  | Log defects in JIRA with severity/priority, assign to dev, track till closure.
Step 9 | Sanity, Re-testing & Regression Testing |  | After bug fixes: sanity check → retest fixed bugs → regression on impacted areas.
Step 10 | Test Sign Off |  | Prepare Test Summary Report, get sign-off from stakeholders for go-live.

## Step1 - Introduction
STEP 1 — Project Introduction
Project Background
The Banking Application is a comprehensive digital banking platform that provides retail and corporate customers access to banking services via web and mobile interfaces. The QA team is responsible for validating all core banking functionalities before production release.
Project Scope
IN SCOPE: User Login & Authentication, Fund Transfer (NEFT/IMPS/UPI), Account Balance & Statements, Bill Payments, Loan Application, Fixed Deposits, ATM/Card Management, Profile Management, Notifications, Cheque Services, Session Management, Performance & Accessibility. OUT OF SCOPE: Backend database testing, load testing beyond 3G simulation, third-party payment reconciliation.
Objectives
1. Validate all 15 banking features against business requirements. 2. Identify and report defects before UAT sign-off. 3. Ensure security vulnerabilities are tested (OWASP Top 10). 4. Achieve 100% test case execution with <5% critical defect escape rate.
Stakeholders
Product Owner: Mr. Rajesh Kumar Business Analyst: Ms. Priya Sharma Dev Lead: Mr. Arjun Nair QA Lead: Ms. Kavitha Reddy Project Manager: Mr. Suresh Patel
Assumptions & Risks
ASSUMPTIONS: SRS document is final. Test data will be provided by the BA team. JIRA access granted to all QA members. RISKS: Delayed build delivery may impact test schedule. Environment instability in SIT. Incomplete test data for loan module.
Entry & Exit Criteria
ENTRY: Build deployed, smoke test passed, test cases reviewed & approved. EXIT: 100% test execution, 0 critical open defects, UAT sign-off obtained, Test Summary Report approved.

## Step2 - Functionality
STEP 2 — Understanding & Exploring Functionality → Documentation
# | Feature Module | Sub-Features / User Flows | User Roles | Integration Points | Priority
1 | User Login & Auth | Login with credentials, OTP 2FA, CAPTCHA, Account lockout, Password reset, Remember device | Customer, Admin | Active Directory, OTP Gateway | Critical
2 | Fund Transfer | Own account transfer, NEFT, RTGS, IMPS, Add beneficiary, Transfer limits | Customer | NEFT/RTGS Clearing, CBS Core | Critical
3 | UPI Payments | Send/Receive via UPI ID, QR code scan, MPIN validation, UPI lite | Customer | NPCI UPI Switch | Critical
4 | Account Balance | Savings/Current/FD balance view, Mini statement, Available vs. ledger balance | Customer, RM | CBS Core System | High
5 | Account Statement | View/Download PDF/Excel, Date range filter, Transaction search | Customer | Report Engine, PDF Generator | High
6 | Bill Payment | Electricity, Water, Gas, DTH, Mobile recharge, Insurance premium | Customer | BBPS Gateway, Billers API | High
7 | Loan Application | Personal, Home, Car loan apply, EMI calculator, Document upload, Status tracking | Customer, Loan Officer | Loan Origination System | High
8 | Fixed Deposits | Create FD, View FD details, Premature closure, Auto-renewal, FD certificate | Customer | CBS FD Module | Medium
9 | Profile Management | Update contact info, Change password, KYC update, Nominee management | Customer | KYC System, CRM | Medium
10 | Cheque Services | Cheque book request, Stop cheque, Cheque status enquiry, Positive pay | Customer | Cheque Clearing System | Low
11 | ATM/Card Management | Block/Unblock card, Change ATM PIN, Set transaction limits, Virtual card | Customer | Card Management System | Critical
12 | Notifications | SMS, Email, Push alerts for all transactions, OTP, Offers, Balance alerts | Customer | SMS Gateway, Email Server | High
13 | Session Management | Auto logout, Concurrent session control, Session token expiry | Customer, Admin | Auth Server | Critical
14 | Performance | Page load times on 3G/4G, Response time for transactions, App crash rate | All | APM Tools | Medium
15 | Accessibility | WCAG 2.1 compliance, Screen reader support, Keyboard navigation | All Users | N/A | Low

## Step3 - Test Plan
STEP 3 — Test Plan & Effort Estimation
Test Plan ID |  |  | TP-BANK-2026-001
Project |  |  | Banking Application v1.0
Prepared By |  |  | QA Lead — Kavitha Reddy
Reviewed By |  |  | Project Manager — Suresh Patel
Date |  |  | April 2026
Version |  |  | 1.0
Effort Estimation by Feature
# | Feature | Test Scenarios | Test Cases | Estimated Hrs | Actual Hrs | Status
1 | User Login & Auth | 5 | 8 | 8 | 8 | Completed
2 | Fund Transfer | 6 | 10 | 12 | 11 | Completed
3 | UPI Payments | 4 | 6 | 6 | 6 | Completed
4 | Account Balance | 2 | 3 | 3 | 3 | Completed
5 | Account Statement | 3 | 4 | 4 | 4 | Completed
6 | Bill Payment | 4 | 6 | 6 | 6 | Completed
7 | Loan Application | 5 | 8 | 10 | 9 | Completed
8 | Fixed Deposits | 4 | 6 | 6 | 5 | Completed
9 | Profile Management | 3 | 4 | 4 | 4 | Completed
10 | Cheque Services | 2 | 3 | 3 | 3 | Completed
11 | ATM/Card Management | 4 | 6 | 6 | 6 | Completed
12 | Notifications | 3 | 4 | 4 | 4 | Completed
13 | Session Management | 2 | 3 | 3 | 3 | Completed
14 | Performance | 2 | 3 | 4 | 4 | Completed
15 | Accessibility | 1 | 2 | 2 | 2 | Completed
| TOTAL | 50 | 76 | 81 | 78

## Step4 - Test Scenarios
STEP 4 — Test Scenarios
Scenario ID | Feature | Test Scenario | Type | Priority | Coverage
TS-001 | User Login | Verify valid login with correct username and password | Positive | High | Functional
TS-002 | User Login | Verify login fails with incorrect credentials | Negative | High | Functional
TS-003 | User Login | Verify account locks after 3 consecutive failed attempts | Negative | High | Security
TS-004 | User Login | Verify 2FA OTP is sent and accepted correctly | Positive | High | Security
TS-005 | Fund Transfer | Verify successful fund transfer between own accounts | Positive | High | Functional
TS-006 | Fund Transfer | Verify NEFT transfer to external bank account | Positive | High | Integration
TS-007 | Fund Transfer | Verify transfer is rejected when amount exceeds daily limit | Negative | High | Boundary
TS-008 | Fund Transfer | Verify transfer fails with insufficient balance | Negative | High | Functional
TS-009 | UPI Payment | Verify UPI payment to valid UPI ID with correct MPIN | Positive | High | Functional
TS-010 | UPI Payment | Verify UPI payment blocked on wrong MPIN entry | Negative | High | Security
TS-011 | Account Balance | Verify account balance is displayed correctly | Positive | High | Functional
TS-012 | Account Statement | Verify statement download in PDF for custom date range | Positive | Medium | Functional
TS-013 | Bill Payment | Verify successful bill payment with sufficient balance | Positive | High | Integration
TS-014 | Bill Payment | Verify bill payment fails with insufficient balance | Negative | High | Functional
TS-015 | Loan Application | Verify loan application form submission with valid data | Positive | High | Functional
TS-016 | Loan Application | Verify EMI calculator produces correct values | Positive | Medium | Functional
TS-017 | Fixed Deposit | Verify new FD creation with valid amount and tenure | Positive | Medium | Functional
TS-018 | Fixed Deposit | Verify premature FD closure calculates penalty correctly | Negative | Medium | Functional
TS-019 | Profile Update | Verify mobile number update with OTP verification | Positive | Medium | Functional
TS-020 | ATM/Card Mgmt | Verify debit card can be blocked immediately on request | Positive | High | Functional
TS-021 | ATM/Card Mgmt | Verify ATM PIN change with correct old PIN | Positive | High | Security
TS-022 | Notifications | Verify SMS alert received within 30 sec of transaction | Positive | High | Functional
TS-023 | Session Mgmt | Verify session auto-expires after 5 minutes of inactivity | Positive | High | Security
TS-024 | Performance | Verify login page loads within 5 seconds on 3G network | Positive | Medium | Performance
TS-025 | Accessibility | Verify all screen elements are readable by screen reader | Positive | Low | Accessibility

## Step5 - Test Cases
STEP 5 — Detailed Test Cases & Review
TC ID | Feature | Scenario | Pre-conditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Priority | Type | Severity | Environment | Remarks
TC-001 | User Login | Valid login | App open, network active | 1. Navigate to login page 2. Enter valid email 3. Enter correct password 4. Click Login | Email: user@bank.com Pass: Test@123 | Dashboard loads, welcome message shown | Dashboard loaded | Pass | High | Functional | Critical | UAT | Smoke test case
TC-002 | User Login | Invalid password | App open | 1. Navigate to login 2. Enter valid email 3. Enter wrong password 4. Click Login | Email: user@bank.com Pass: Wrong999 | Error: 'Invalid credentials' displayed | Error shown | Pass | High | Functional | Critical | UAT | Negative test
TC-003 | User Login | Account lockout | Valid account exists | 1. Enter wrong password 3 times consecutively 2. Check for lockout message | 3 wrong attempts | Account locked, lockout message displayed | Account locked | Pass | High | Security | Critical | SIT | Security - lockout policy
TC-004 | Fund Transfer | Own account transfer | Login complete, 2 accounts | 1. Go to Transfer 2. Select From: Savings 3. Select To: Current 4. Enter ₹5,000 5. Click Submit | From: SAV001 To: CUR001 Amt: ₹5,000 | Success msg + reference number, balance updated | Transfer success | Pass | High | Functional | Critical | UAT | Core banking flow
TC-005 | Fund Transfer | NEFT transfer | Beneficiary added | 1. Go to NEFT 2. Select beneficiary 3. Enter ₹10,000 4. Confirm | IFSC: HDFC0001234 Amt: ₹10,000 | Transaction pending/success with ref no. | Ref no generated | Pass | High | Integration | Critical | SIT | IFSC validation needed
TC-006 | Fund Transfer | Exceed daily limit | Daily limit = ₹2,00,000 | 1. Go to Transfer 2. Enter amount above daily limit 3. Submit | Amt: ₹5,00,000 | Error: 'Daily transaction limit exceeded' | Error shown | Pass | High | Functional | High | UAT | Boundary value test
TC-007 | UPI Payment | UPI to valid ID | UPI registered, MPIN set | 1. Go to UPI Pay 2. Enter UPI ID 3. Enter amount 4. Enter MPIN 5. Confirm | UPI: friend@okaxis Amt: ₹500 MPIN: 1234 | Payment success, debit notification | Payment success | Pass | High | Functional | Critical | UAT | Real-time payment
TC-008 | UPI Payment | Wrong MPIN | UPI registered | 1. Go to UPI Pay 2. Enter valid UPI ID 3. Enter wrong MPIN | UPI: test@upi Wrong MPIN: 0000 | Error: 'Incorrect MPIN', retry option | Error shown | Pass | High | Security | Critical | SIT | Security - MPIN validation
TC-009 | Account Balance | View balance | Login complete | 1. Go to Accounts 2. Select Savings Account 3. Click Balance | Account: SAV001 | Available balance and ledger balance shown | Balance displayed | Pass | High | Functional | High | UAT | Core feature
TC-010 | Account Statement | Download PDF | Login complete | 1. Go to Statements 2. Select date range 3. Choose PDF 4. Click Download | From: 01-Jan-2026 To: 31-Mar-2026 | PDF file downloaded with all transactions | PDF downloaded | Pass | Medium | Functional | High | UAT | Verify PDF content
TC-011 | Bill Payment | Pay electricity bill | Login, BESCOM added | 1. Go to Bill Pay 2. Select BESCOM 3. Enter consumer no. 4. Enter amount 5. Pay | Consumer: 12345678 Amt: ₹2,400 | Bill paid, receipt with ref no. shown | Payment confirmed | Pass | High | Integration | High | UAT | Third-party BBPS
TC-012 | Bill Payment | Insufficient balance | Login complete | 1. Go to Bill Pay 2. Enter bill amount > balance 3. Submit | Bill: ₹10,000 Balance: ₹2,000 | Error: 'Insufficient funds' | Error shown | Pass | High | Functional | Critical | SIT | Negative test
TC-013 | Loan Application | Apply personal loan | Login, KYC complete | 1. Go to Loans 2. Select Personal Loan 3. Fill application 4. Upload docs 5. Submit | Amt: ₹1,00,000 Tenure: 24mo Income: ₹50,000 | Application submitted, Loan ID generated | Loan ID generated | Pass | High | Functional | High | UAT | End-to-end flow
TC-014 | Fixed Deposit | Create new FD | Login, savings balance ≥ ₹50,000 | 1. Go to FD 2. Enter ₹50,000 3. Select 12 months 4. Choose payout: Monthly 5. Confirm | Principal: ₹50,000 Tenure: 12 months Rate: 7.5% | FD created, FD certificate generated | FD created | Pass | Medium | Functional | High | UAT | Interest calculation check
TC-015 | ATM/Card Mgmt | Block debit card | Login, active card | 1. Go to Cards 2. Select Debit Card ending 4567 3. Click Block 4. Select reason 5. Confirm | Card: ****4567 | Card blocked immediately, SMS confirmation | Card blocked | Pass | High | Functional | Critical | UAT | Critical security action
TC-016 | ATM/Card Mgmt | Change ATM PIN | Login, active card | 1. Go to Cards 2. Click Change PIN 3. Enter old PIN 4. Enter new PIN 5. Confirm | Old PIN: 1234 New PIN: 5678 | PIN changed successfully, confirmation shown | PIN changed | Pass | High | Security | High | SIT | Encrypted channel verify
TC-017 | Profile Update | Update mobile number | Login complete | 1. Go to Profile 2. Edit mobile no. 3. Enter new number 4. Enter OTP 5. Save | New Mobile: 9876543210 OTP: 456789 | Mobile updated, SMS confirmation sent | Mobile updated | Pass | Medium | Functional | Medium | UAT | OTP flow validation
TC-018 | Notifications | SMS on debit | Login, valid mobile linked | 1. Perform ₹1,000 debit transaction 2. Check registered mobile for SMS | Debit: ₹1,000 from SAV001 | SMS received within 30 seconds of transaction | SMS received | Pass | High | Functional | High | UAT | Real-time alert
TC-019 | Session Mgmt | Auto logout | Login complete | 1. Login successfully 2. Leave app idle for 5 minutes 3. Try to perform any action | Idle time: 5 minutes | 'Session expired' shown, redirected to login | Session expired | Pass | High | Security | High | SIT | Timeout policy
TC-020 | Performance | 3G login speed | 3G network throttled | 1. Set network to 3G 2. Navigate to login page 3. Enter credentials 4. Time the load | Network: 3G ~1Mbps Benchmark: <5 sec | Login page and dashboard load within 5 seconds | Loaded in 4.2s | Pass | Medium | Performance | Medium | UAT | Performance benchmark
TC-021 | Fixed Deposit | Premature closure | Active FD 6 months old | 1. Go to FD section 2. Select active FD 3. Request premature closure 4. Confirm | FD: 6 months (12-mo tenure) Penalty: 1% | Closure processed with 1% penalty, net amount shown | Closure processed | Pass | Medium | Functional | High | SIT | Penalty calculation
TC-022 | User Login | 2FA OTP login | OTP service active | 1. Enter valid credentials 2. Wait for OTP SMS 3. Enter OTP within 2 mins 4. Login | User: user@bank.com OTP: 345678 | Successful login after OTP verification | Login success | Pass | High | Security | High | UAT | 2FA validation
TC-023 | Fund Transfer | IMPS instant transfer | Login, beneficiary added | 1. Go to IMPS transfer 2. Select beneficiary 3. Enter ₹15,000 4. Confirm | Beneficiary: IMPS enabled Amt: ₹15,000 | Transfer completed instantly, ref no. shown | IMPS success | Pass | High | Integration | Critical | SIT | 24x7 IMPS check
TC-024 | Cheque Services | Request cheque book | Login, savings account | 1. Go to Cheque Services 2. Select Request Cheque Book 3. Select 25 leaves 4. Submit | Account: SAV001 Leaves: 25 | Request submitted, tracking ID generated | Request placed | Pass | Low | Functional | Medium | UAT | Postal delivery
TC-025 | Accessibility | Screen reader test | Screen reader enabled | 1. Enable TalkBack/VoiceOver 2. Navigate Login → Balance → Transfer screens | Screen reader: TalkBack (Android) | All buttons, labels, and fields are announced correctly | All labels read | Pass | Low | Accessibility | Low | UAT | WCAG 2.1 AA

## Step6 - Environment
STEP 6 — Environment Setup & Build Deployment
Parameter | SIT Environment | UAT Environment | Production (Ref)
Environment | SIT (System Integration Testing) | UAT (User Acceptance Testing) | Production (Reference)
URL | https://sit.bankingapp.internal | https://uat.bankingapp.internal | https://app.mybank.com
Server | Linux RHEL 8 — 16GB RAM | Linux RHEL 8 — 32GB RAM | Cloud AWS — Auto Scale
Database | Oracle 19c — SIT Schema | Oracle 19c — UAT Schema | Oracle 19c — PROD
Browser Support | Chrome 120+, Firefox 118+ | Chrome 120+, Firefox 118+, Safari 16+ | All modern browsers
Mobile OS | Android 12, iOS 15 | Android 12+, iOS 15+ | Android 10+, iOS 14+
Build Version | v1.0.0-SIT-RC3 | v1.0.0-UAT-RC1 | v1.0.0 (Post sign-off)
Smoke Test Status | Pass ✅ | Pass ✅ | N/A
Deployment Date | 10-Apr-2026 | 11-Apr-2026 | Post UAT sign-off
Admin Access | qa_admin / QA@sit#2026 | qa_uat / QA@uat#2026 | Restricted
Test Data | Synthetic data by BA team | Masked production data | Real data
Environment Owner | DevOps Team | UAT Lead + BA | Prod Support Team
Smoke Test Checklist
Check ID | Smoke Test Item | Status | Date
STK-001 | Application URL accessible | Pass | 10-Apr-2026
STK-002 | Login page loads correctly | Pass | 10-Apr-2026
STK-003 | Valid login works | Pass | 10-Apr-2026
STK-004 | Dashboard renders without errors | Pass | 10-Apr-2026
STK-005 | Account balance API responding | Pass | 10-Apr-2026
STK-006 | Fund transfer page accessible | Pass | 10-Apr-2026
STK-007 | Database connectivity confirmed | Pass | 10-Apr-2026
STK-008 | SMS gateway connectivity | Pass | 10-Apr-2026

## Step7 - Execution
STEP 7 — Test Execution Report
TC ID | Feature | Tester | Exec Date | Build Ver. | Status | Defect ID | Comments
TC-001 | User Login | Kavitha R. | 10-Apr-2026 | v1.0-RC3 | Pass | — | Smoke test
TC-002 | User Login | Kavitha R. | 10-Apr-2026 | v1.0-RC3 | Pass | — | Negative test
TC-003 | User Login | Kavitha R. | 10-Apr-2026 | v1.0-RC3 | Pass | — | Lockout verified
TC-004 | Fund Transfer | Ravi K. | 10-Apr-2026 | v1.0-RC3 | Pass | — | Core flow
TC-005 | Fund Transfer | Ravi K. | 10-Apr-2026 | v1.0-RC3 | Pass | — | NEFT verified
TC-006 | Fund Transfer | Ravi K. | 10-Apr-2026 | v1.0-RC3 | Pass | — | Boundary test
TC-007 | UPI Payment | Sneha M. | 11-Apr-2026 | v1.0-RC3 | Pass | — | Payment success
TC-008 | UPI Payment | Sneha M. | 11-Apr-2026 | v1.0-RC3 | Pass | — | Security check
TC-009 | Account Balance | Kavitha R. | 11-Apr-2026 | v1.0-RC3 | Pass | — | Balance correct
TC-010 | Account Statement | Kavitha R. | 11-Apr-2026 | v1.0-RC3 | Pass | — | PDF verified
TC-011 | Bill Payment | Ravi K. | 11-Apr-2026 | v1.0-RC3 | Pass | — | BBPS integration
TC-012 | Bill Payment | Ravi K. | 11-Apr-2026 | v1.0-RC3 | Pass | — | Insufficient bal
TC-013 | Loan Application | Sneha M. | 11-Apr-2026 | v1.0-RC3 | Pass | — | Loan ID generated
TC-014 | Fixed Deposit | Sneha M. | 11-Apr-2026 | v1.0-RC3 | Pass | — | FD created
TC-015 | ATM/Card Mgmt | Kavitha R. | 11-Apr-2026 | v1.0-RC3 | Pass | — | Card blocked
TC-016 | ATM/Card Mgmt | Kavitha R. | 11-Apr-2026 | v1.0-RC3 | Pass | — | PIN changed
TC-017 | Profile Update | Ravi K. | 11-Apr-2026 | v1.0-RC3 | Pass | — | OTP flow ok
TC-018 | Notifications | Ravi K. | 11-Apr-2026 | v1.0-RC3 | Pass | — | SMS in 10 sec
TC-019 | Session Mgmt | Sneha M. | 11-Apr-2026 | v1.0-RC3 | Pass | — | Timeout works
TC-020 | Performance | Kavitha R. | 11-Apr-2026 | v1.0-RC3 | Pass | — | 4.2s on 3G
TC-021 | Fixed Deposit | Ravi K. | 11-Apr-2026 | v1.0-RC3 | Pass | — | Penalty correct
TC-022 | User Login | Kavitha R. | 11-Apr-2026 | v1.0-RC3 | Pass | — | 2FA success
TC-023 | Fund Transfer | Ravi K. | 11-Apr-2026 | v1.0-RC3 | Pass | — | IMPS instant
TC-024 | Cheque Services | Sneha M. | 11-Apr-2026 | v1.0-RC3 | Pass | — | Request placed
TC-025 | Accessibility | Sneha M. | 11-Apr-2026 | v1.0-RC3 | Pass | — | WCAG compliant
EXECUTION SUMMARY |  |  |  |  | 25 | 25/25 Passed — 100% Pass Rate

## Step8 - Bug Report
STEP 8 — Bug Reporting & Tracking
Bug ID | Feature | Bug Title | Steps to Reproduce | Expected | Actual | Severity | Priority | Status | Assigned To
BUG-001 | User Login | Account not locked after 3 failed attempts in some browsers | 1. Use Firefox 2. Enter wrong password 3 times 3. Observe | Account should lock | Account remains active — no lockout | Critical | High | Fixed | Dev: Arjun N.
BUG-002 | UPI Payment | MPIN accepted even after 5 wrong entries without blocking UPI | 1. Enter wrong MPIN 5 times 2. Observe behavior | UPI blocked after 3 wrong MPINs | UPI not blocked — no limit enforced | Critical | High | Fixed | Dev: Priya S.
BUG-003 | Fund Transfer | Beneficiary name not displayed in NEFT confirmation screen | 1. Initiate NEFT to beneficiary 2. Go to confirmation screen | Beneficiary name shown | Only account number shown, name missing | Major | Medium | Fixed | Dev: Arjun N.
BUG-004 | Account Statement | PDF statement shows wrong date format (MM/DD instead of DD/MM) | 1. Download PDF statement 2. Check transaction dates | Date: DD/MM/YYYY | Date shown as MM/DD/YYYY | Minor | Low | Fixed | Dev: Ravi K.
BUG-005 | Notifications | SMS alert delayed by over 5 minutes for NEFT transactions | 1. Do NEFT transfer 2. Wait for SMS 3. Record time | SMS in <30 seconds | SMS arrived after 7 minutes | Major | High | Fixed | Dev: Infra Team
BUG-006 | Loan Application | EMI calculator shows incorrect value for tenures above 36 months | 1. Enter loan ₹5,00,000 2. Select 48 months tenure 3. Calculate EMI | Correct EMI shown | EMI figure is wrong — off by 20% | Major | High | Fixed | Dev: Sneha M.
BUG-007 | Profile Update | Email update allowed without OTP verification | 1. Go to Profile 2. Change email 3. Save without OTP | OTP should be required | Email saved without OTP verification | Critical | High | Fixed | Dev: Security Team
BUG-008 | ATM/Card Mgmt | Card block confirmation SMS not sent after blocking | 1. Block debit card 2. Check registered mobile | SMS confirmation within 1 minute | No SMS received after card block | Minor | Medium | Fixed | Dev: Ravi K.
BUG-009 | Fixed Deposit | Premature closure penalty not calculated correctly | 1. Create 12-month FD 2. Close after 6 months 3. Check penalty | 1% penalty deducted | Penalty not applied — full amount paid | Major | High | Fixed | Dev: Arjun N.
BUG-010 | Session Mgmt | Session does not expire on iOS Safari after inactivity | 1. Login on iOS Safari 2. Leave idle for 10 minutes 3. Tap screen | Session expired, redirect to login | Session still active — no timeout | Critical | High | Fixed | Dev: Mobile Team
BUG-011 | Bill Payment | Bill payment screen crashes on Android 12 for DTH category | 1. Go to Bill Pay on Android 12 2. Select DTH 3. Select provider | Provider list shown | App crashes immediately | Major | High | Fixed | Dev: Mobile Team
BUG-012 | Fund Transfer | Transfer limit validation only checks one direction for IMPS | 1. Set daily limit ₹50,000 2. Try ₹30,000 IMPS twice 3. Second should be blocked | 2nd transfer blocked if total > limit | Both transfers succeeded — limit not cumulative | Critical | High | Fixed | Dev: Priya S.

## Step9 - Regression
STEP 9 — Sanity, Re-testing & Regression Testing
Sanity Testing — Quick Health Check After New Build
Sanity ID | Area Checked | Check Description | Result | Tester | Date
SAN-001 | Login | Verify login works after build deployment | Pass | Kavitha | 11-Apr-2026
SAN-002 | Dashboard | Dashboard loads without JS errors | Pass | Kavitha | 11-Apr-2026
SAN-003 | Fund Transfer | Basic transfer between own accounts | Pass | Ravi | 11-Apr-2026
SAN-004 | Balance | Account balance displays correctly | Pass | Ravi | 11-Apr-2026
SAN-005 | UPI | UPI payment to registered ID works | Pass | Sneha | 11-Apr-2026
SAN-006 | Notifications | SMS alert received on test transaction | Pass | Sneha | 11-Apr-2026
Re-testing — Verify Bug Fixes
Re-test ID | Bug ID | Feature | Fix Verified? | Re-test Result | Tester | Date
RT-001 | BUG-001 | User Login | Yes | Pass | Kavitha | 11-Apr-2026
RT-002 | BUG-002 | UPI Payment | Yes | Pass | Sneha | 11-Apr-2026
RT-003 | BUG-003 | Fund Transfer | Yes | Pass | Ravi | 11-Apr-2026
RT-004 | BUG-006 | Loan Application | Yes | Pass | Sneha | 11-Apr-2026
RT-005 | BUG-007 | Profile Update | Yes | Pass | Kavitha | 11-Apr-2026
RT-006 | BUG-009 | Fixed Deposit | Yes | Pass | Ravi | 11-Apr-2026
RT-007 | BUG-010 | Session Mgmt | Yes | Pass | Kavitha | 11-Apr-2026
RT-008 | BUG-012 | Fund Transfer | Yes | Pass | Ravi | 11-Apr-2026
Regression Testing — Impacted Areas After Fixes
Reg ID | Impacted Feature | Test Case Executed | Regression Result | Tester | Date | Notes
REG-001 | User Login | TC-001,TC-002,TC-003 | Pass | Kavitha | 11-Apr-2026 | Auth module regression
REG-002 | Fund Transfer | TC-004,TC-005,TC-006 | Pass | Ravi | 11-Apr-2026 | Transfer limits re-verified
REG-003 | UPI Payment | TC-007,TC-008 | Pass | Sneha | 11-Apr-2026 | MPIN security re-checked
REG-004 | Profile Update | TC-017 | Pass | Kavitha | 11-Apr-2026 | OTP bypass fix verified
REG-005 | Fixed Deposit | TC-014,TC-021 | Pass | Ravi | 11-Apr-2026 | Penalty calculation fixed
REG-006 | Session Mgmt | TC-019 | Pass | Sneha | 11-Apr-2026 | iOS Safari timeout fixed
REG-007 | Notifications | TC-018,TC-022 | Pass | Kavitha | 11-Apr-2026 | SMS delivery verified

## Step10 - Sign Off
STEP 10 — Test Sign Off & Summary Report
Test Execution Summary
Total Test Cases |  |  | 25
Executed |  |  | 25
Passed |  |  | 25
Failed |  |  | 0
Blocked |  |  | 0
Not Executed |  |  | 0
Pass % |  |  | 100%
Critical Defects Open |  |  | 0
Total Defects Logged |  |  | 12
Total Defects Fixed |  |  | 12
Defect Fix Rate |  |  | 100%
Test Summary Observations
• All 25 test cases executed successfully across 15 banking features.
• 12 defects identified during testing — all 12 fixed and verified before sign-off.
• Critical security issues (account lockout bypass, MPIN limit bypass, email OTP bypass) were found and fixed.
• Performance benchmark met: login page loads in 4.2 seconds on 3G network (target: <5s).
• Accessibility tested per WCAG 2.1 AA standards — all screen reader labels verified.
• Regression testing completed — no new defects introduced after bug fixes.
• All 3rd-party integrations (BBPS, UPI, NEFT, SMS Gateway) verified in SIT and UAT.
Sign-Off Approval
Role | Name | Signature | Date | Remarks
QA Lead | Kavitha Reddy | ✅ Approved | 11-Apr-2026 | Test execution complete
Business Analyst | Priya Sharma | ✅ Approved | 11-Apr-2026 | Requirements met
Product Owner | Rajesh Kumar | ✅ Approved | 11-Apr-2026 | UAT sign-off granted
Project Manager | Suresh Patel | ✅ Approved | 11-Apr-2026 | Go-live approved
Dev Lead | Arjun Nair | ✅ Approved | 11-Apr-2026 | All defects fixed
🎉 PROJECT SUCCESSFULLY COMPLETED — CLEARED FOR PRODUCTION DEPLOYMENT